## General
The Friends of Headstone Manor Park - Annual Action Plan (01st Jamuary 2024 to 31st December 2024)
General
Item | Objective | Item | Description | Resources Required | Approval
[5 empty] | Harrow Parks Forum | Community Engagement | Parks | Infastructure
1 | Establish / Improve online prescence | A | Facebook page should be enhanced to reach out to those that have liked and / or viewing the page | FoHMP | N/A | N/A | N/A | N/A
|  | B | Website to be enhanced to send out Events via mail shoot | FoHMP | N/A | N/A | N/A | N/A
2 | Increase membership / fill key Committee positions |  | Leaflet drop in surrounding area | FoHMP | N/A | N/A | N/A | N/A
3 | Socialising Plans and Consultation with Residents & Park Users |  | Gauge local opinion before making any changes, Parrticullary in the case of Hedgeing at the bottom of gardens or planting trees that may eventually cast shadows into gardens | FoHMP | N/A |  | N/A | N/A
4 | Seek funding for some new hedgeing via the Close the Gap Community Hedge Fund |  | Determine areas in need of new hedgeing and cost a realistic length of hedgeing to fill these gaps | FoHMP
5 | Research funds available for Community Trees |  | Establish viable number of trees in conjunction with Harrow Tree Officer | FoHMP
6 | Reasearch funds available for new Benches and Bins |  | Establish possible sites for New Benches and Bins and discuss with Harrow Council | FoHMP

## Work Plan
The Friends of Headstone Manor Park - Annual Action Plan (01st Jamuary 2024 to 31st December 2024)
Work Plan
Item | Objective | Item | Description | Resources Required | Approval
[5 empty] | Harrow Parks Forum | Community Engagement | Parks | Infastructure
1 | The Moat Café Wild Flower Meadow |  | Provision of Wild Flower Meadow from the Public Toilet Block to the Bridge to Bessbourgh Cricket Club | FoHMP | N/A | Yes (Included in MMP) | Yes (Included in MMP) | Yes (Included in MMP)
2 | The Yeading Brooke Grove |  | Provision of Native Bulbs and Wild Flowers along the Brooke edge from the Picnic area to Hugs and Giggles Nursery | FoHMP | N/A | Yes (Included in MMP) | Yes (Included in MMP) | Yes (Included in MMP)
3 | Pinner View Wildlife Area |  | Mowing regime modfied in 5 Year Management & Maintenance Plan | FoHMP | N/A | Yes (Included in MMP) | Yes (Included in MMP) | Yes (Included in MMP)
4 | John Hollingdale Grove |  | Provision of Native Perennial & Annual Bulbs along with shrubs to atract Pollinators, Moths & Butterflies | FoHMP | N/A | Yes (Included in MMP) | Yes (Included in MMP) | Yes (Included in MMP)
5 | Parkside Way Entrance |  | Improvement to Entrance Drought tollerant plants as 6 No. Ornamental Cherry Trees | FoHMP / Harrow Council | N/A | Yes (UKSPF 2023 / 2024) | Yes (UKSPF 2023 / 2024) | Yes (UKSPF 2023 / 2024)
6 | The periphery of Headstone Manor Park there is no vegetation between the park and people's garden fence boundary |  | Plant new hedging in these spots. Should be native species; hawthorn, blackthorn, beech etc. which will improve the overall look of the Park, provide nesting sites for wild birds and provide extra security for householders | FoHMP | N/A | Yes (Included in MMP) | Yes (Included in MMP) | Yes (Included in MMP)
7 | Water Supply for watering new trees and other plants | A | Provision of water supplies across the Park. Harrow Council to investigate | FoHMP / Harrow Counci | N/A
|  | B | Discuss option of providing an outdoor tap at the Moat Café. Requires discussions with Headstone Manor & Museum | FoHMP / Harrow Counci | N/A
|  | C | Provision of Water Butts at Public Toilets for Water harvesting | FoHMP | N/A | Yes (Included in MMP) | Yes (Included in MMP) | Yes (Included in MMP)
8 | Consultation with Residents and Park Users |  | Gauge local opinion before making any changes. Particularly in the case of hedging at the bottom of gardens or planting trees that may eventually cast shadows into gardens | FoHMP / Harrow Counci | N/A
9 | New Bins |  | Bins to be provided to new benches were practicle FoHMP to liase with Harrow Council (2 new bins in Wetland Area & 2 new bins on circular route ) | FoHMP / Harrow Counci | N/A
10 | "Mulch Store" |  | Create a small storeage area for chippings to mulch new trees/bedding plants/bulbs etc. | FoHMP / Harrow Counci | N/A
11 | "Compost Area" |  | Create an area for onsite Composting | FoHMP / Harrow Counci | N/A