## A Welcoming Place
The Friends of Headstone Manor Park - 5 Year Action Plan (01st Jamuary 2023 to 31st December 2027)
A Welcoming Place
Item | Objective | Sub-Item | Description | Current Status | Resources Required | Year |  |  |  |  | Deliverables
[6 empty] | 2023 | 2024 | 2025 | 2026 | 2027
1 | Identify and address physical barriers to accessability of the Pak | A | Are all entrances disabled friendly? | Yes |  | N/A | N/A | N/A | N/A | N/A
2 | Installation of Council Notice Boards. |  | All entrances should have a noticeboard, these should be positioned outside the entrances where practical | See Item A-G | FoHMP / Harrow Council | N/A | N/A | N/A | N/A | N/A
|  | A | Pinner View Entrance | The Noticeboard has been installed approx 20 M from the Moat Café this should be relocated to the Park entrance in Pinner View | FoHMP / Harrow Council | N/A
|  | B | Parkside Way Entrance | No notice board installed | FoHMP / Harrow Council | N/A | N/A |  |  |  | No action required at present potential to install Notice board by Footbridge
|  | C | Headstone Lane Entrance | Location acceptable | FoHMP / Harrow Council | N/A | N/A | N/A | N/A | N/A
|  | D | Headstone Lane West Entrance | No notice board installed | FoHMP / Harrow Council | N/A | N/A |  |  |  | No action required at present
|  | E | West Harrow Housing Development (Footpath 1) | No notice board installed | FoHMP / Harrow Council | N/A | N/A |  |  |  | No action required at present to be reviwed upon completion of works
|  | F | West Harrow Housing Development (Footpath 2) | No notice board installed | FoHMP / Harrow Council | N/A | N/A |  |  |  | No action required at present to be reviwed upon completion of works
|  | G | Green Cycle Route | No notice board installed | FoHMP / Harrow Council | N/A | N/A |  |  |  | No action required at present to be reviwed upon completion of works
3 | Installation of Park interpretation Maps |  | All entrances should have an interpretation Map just inside the entrances where practical | See Item A-G | FoHMP / Harrow Council | N/A | N/A | N/A | N/A | N/A
|  | A | Pinner View Entrance | Map to be amended to indicate correct entrance on Pinner View | FoHMP / Harrow Council | N/A
|  | B | Parkside Way Entrance | Map to be amended to indicate correct entrance on Pinner View | FoHMP / Harrow Council | N/A
|  | C | Headstone Lane Entrance | Map to be amended to indicate correct entrance on Pinner View | FoHMP / Harrow Council | N/A
|  | D | Headstone Lane West Entrance | Map to be amended to indicate correct entrance on Pinner View | FoHMP / Harrow Council | N/A
|  | E | West Harrow Housing Development (Footpath 1) | No interpretation Map installed | FoHMP / Harrow Council | N/A |  |  |  |  | No action required at present to be reviwed upon completion of works 2023
|  | F | West Harrow Housing Development (Footpath 1) | No interpretation Map installed | FoHMP / Harrow Council | N/A |  |  |  |  | No action required at present to be reviwed upon completion of works 2023
|  | G | Green Cycle Route | No interpretation Map installed | FoHMP / Harrow Council | N/A |  |  |  |  | No action required at present to be reviwed upon completion of works 2023
4 | Installation of Park Bye Laws |  | All entrances should have the Bye Laws displayed just inside the entrances where practical | Item A-G | FoHMP / Harrow Council
|  | A | Pinner View Entrance | Laminated Copy in Notice Board | FoHMP / Harrow Council | [5 empty] | Ideally these should be displayed at all Park Entrances (Bye Laws need to be updated by Harrow Council)
|  | B | Parkside Way Entrance | Not Displayed | FoHMP / Harrow Council | [5 empty] | Ideally these should be displayed at all Park Entrances (Bye Laws need to be updated by Harrow Council)
|  | C | Headstone Lane Entrance | Laminated Copy in Notice Board | FoHMP / Harrow Council | [5 empty] | Ideally these should be displayed at all Park Entrances (Bye Laws need to be updated by Harrow Council)
|  | D | Headstone Lane West Entrance | Not Displayed | FoHMP / Harrow Council | [5 empty] | Ideally these should be displayed at all Park Entrances (Bye Laws need to be updated by Harrow Council)
|  | E | West Harrow Housing Development (Footpath 1) | Not Displayed | FoHMP / Harrow Council | [5 empty] | Ideally these should be displayed at all Park Entrances (Bye Laws need to be updated by Harrow Council)
|  | F | West Harrow Housing Development (Footpath 1) | Not Displayed | FoHMP / Harrow Council | [5 empty] | Ideally these should be displayed at all Park Entrances (Bye Laws need to be updated by Harrow Council)
|  | G | Green Cycle Route | Not Displayed | FoHMP / Harrow Council | [5 empty] | Ideally these should be displayed at all Park Entrances (Bye Laws need to be updated by Harrow Council)
5 | Childrens Playground | A | Childrens Playground Signage is out of date | New Signage to be installed | Harrow Council
|  | B | No Dogs allowed signage to be displayed | No Signage at present | Harrow Council
|  | C | No Bicycle signage to be displayed | No Signage at present | Harrow Council
6 | Improvement to Pinner View Entrance | A | Wildflower areas to be cut annually, front of Earth mounds to be kept strimmed as requested by Headstone Manor & Museum | Refer to MMP | FoHMP / Harrow Council
| Improvement to Parkside Way Entrance | B | FoHMP to submit planting plan including 6 No. Ornamental Cherry Trees | Refer to MMP | FoHMP / Harrow Council
| Improvement to Headstone Lane Entrance | C | Wildflower areas to be cut annually | Refer to MMP | FoHMP / Harrow Council
| Improvement to Headstone Lane West | D | Vechile incursion boulders to be installed | Refer to MMP | Harrow Council
| Improvement to West Harrow Housing Development (Footpath 1) | E | Wildflower areas to be cut annually | Refer to MMP | FoHMP / Harrow Council
| Improvement to West Harrow Housing Development (Footpath 2) | F | Wildflower areas to be cut annually | Refer to MMP | FoHMP / Harrow Council
| Improvement to Green Cycle Route | G | Wildflower areas to be cut annually | Refer to MMP | FoHMP / Harrow Council

## Heritage & Conservation
The Friends of Headstone Manor Park - 5 Year Action Plan (01st Jamuary 2023 to 31st December 2027)
Heratige & Conservation
Item | Objective | Sub-Item | Description | Current Status | Resources Required | Year |  |  |  |  | Deliverables
[6 empty] | 2023 | 2024 | 2025 | 2026 | 2027
1 | Provision of Social Media outlets for Park | A |  | See Community Involvement Section | [6 empty] | Ongoing
|  |  | Facebook | See Community Involvement Section | [6 empty] | Ongoing
|  |  | Twitter | See Community Involvement Section | [6 empty] | Ongoing
|  |  | Instargam | See Community Involvement Section | [6 empty] | Ongoing
|  |  | Website | See Community Involvement Section | [6 empty] | Ongoing
|  |  | Noticeboards | See Community Involvement Section | [6 empty] | Ongoing

## Clean & Well Maintained
The Friends of Headstone Manor Park - 5 Year Action Plan (01st Jamuary 2023 to 31st December 2027)
Clean & Well Maintained
Item | Objective | Sub-Item | Description | Current Status | Resources Required | Year |  |  |  |  | Deliverables
[6 empty] | 2023 | 2024 | 2025 | 2026 | 2027
1 | Grass Cutting Regime |  | Harrow Council undertake an effective 3 week cycle for cutting both large and small areas of grass. See Management & Maintenance Plan for details | ongoing with a review each January | FoHMP / Harrow Council
2 | Tree Pollarding / Pruning | A | The trees are a main attraction of the park , however many of them are to tall and / or have lots of very large dead branches that would present a significant hazzard if they were to fall | Harrow Council have a 5 year rolling maintenance programme where every registered tree is assessed for safety issues with action being taken as neccesary | FoHMP / Harrow Council | [5 empty] | FoHMP have requested latest copy of Tree schedule
|  | B | Minor Pruning should be carried out so that branches no longer reach the ground and / or do not encroach onto footpaths. Also to include control of any newly planted Hedging ( see Development ) | Harrow Council do not have a budget to do this. FoHMP, to monitor and undertake minor pruning 2 times per year | FoHMP
3 | Litter Collection | A | Harrow Council undertake this on a Twice weekly basis | Additional bins required for the additional benches installed in 2022 | FoHMP / Harrow Council
|  | B | Supplementary litter picking should be undertaken by the FoHMP | Harrow Council have provide Litter Pickers, Bags and Gloves for this acivity | FoHMP | [5 empty] | FoHMP hold regular Litter Picking events on Volunteering days
4 | Potential Flooding | A | Swales to be kept clear of leaf material and litter to prevent flooding of footpaths |  | FoHMP | [5 empty] | FoHMP to include on Voluteering Day Activities
|  | B | Sections of Footpath within the Wetland area requires additional work to prevent footpath flooding in poor weather | Harrow Council / Ground Control have undertaken some remedial works as part of there snagging / defects | Harrow Council / Ground Control | [5 empty] | To be reviewed in Spring 2023
5 | Watering and Mulching of New Trees |  | Orchard trees require regular watering until 2024 | Harrow Council are rresponsible for this item | Harrow Council / Ground Control | [5 empty] | FoHMP have undertaken Mulching in December 2022

## Community Involement
The Friends of Headstone Manor Park - 5 Year Action Plan (01st Jamuary 2023 to 31st December 2027)
Community Involvement
Item | Objective | Sub-Item | Description | Current Status | Resources Required | Year |  |  |  |  | Deliverables
[6 empty] | 2023 | 2024 | 2025 | 2026 | 2027
1 | Improve online presecence | A | Facebook page should be enhanced to reach out to those likeing and / or viewing the page | Facebook Page in place and being updated with news/photos | FoHMP | [5 empty] | Ongoing
|  | B | Park Website to be Finalised | Website framework is now in place and is currently being updated | FoHMP / Web Designer | [5 empty] | Target Date May 2023
|  | C | Park Twitter Acoount to be developed |  | FoHMP | [5 empty] | To be reviewed by FoHMP Committee
|  | D | Park Instrgram account to be developed | Instagram in place and being updated with news/photos | FoHMP | [5 empty] | Ongoing
2 | Increase Membership |  | Leaflet drop should be conducted in surrounding areas |  | FoHMP | [5 empty] | Ongoing
3 | Development Plans |  | Leaflet drop should be conducted in surrounding areas as well as Website/Facebook articles |  | FoHMP | [5 empty] | Ongoing

## Health Safe & Secure
The Friends of Headstone Manor Park - 5 Year Action Plan (01st Jamuary 2023 to 31st December 2027)
Health, Safe & Secure
Item | Objective | Sub-Item | Description | Current Status | Resources Required | Year |  |  |  |  | Deliverables
[6 empty] | 2023 | 2024 | 2025 | 2026 | 2027
1 | Ensure latest copy of Harrow Parks Forum - Health & Safety Policy is available |  | FoHMP - Health & Safety Policy to be developed along Harrow Park Forum Guidelines | Latest Update August 2022 | Harrow Parks Forum / Park User Group | [5 empty] | Document to be updated at AGM - May 2023
2 | Ensure latest copy of Harrow Parks Forum - Children & Vulnerable Adults Protection Policy is available |  | FoHMP - Children & Vulnerable Adults Protection Policy to be developed along Harrow Park Forum Guidelines | Latest Update August 2022 | Harrow Parks Forum / Park User Group | [5 empty] | Document to be updated at AGM - May 2023
3 | Ensure latest copy of Harrow Parks Forum - Equality & Diversity Policy is available |  | FoHMP - Equality & Diversity Policy to be developed along Harrow Park Forum Guidelines | Latest Update August 2022 | Harrow Parks Forum / Park User Group | [5 empty] | Document to be updated at AGM - May 2023
4 | Ensure latest copy of Harrow Parks Forum - Safe System of Works Sharps Policy is available |  | FoHMP - Safe System of Works Sharps Policy to be developed along Harrow Park Forum Guidelines | Latest Update August 2022 | Harrow Parks Forum / Park User Group | [5 empty] | Document to be updated at AGM - May 2023
5 | Ensure latest copy of Harrow Parks Forum - Risk Assessment template is available |  | FoHMP - Risk Assessment to be developed along Harrow Park Forum Guidelines | Latest Update August 2022 | Harrow Parks Forum / Park User Group | [5 empty] | Document to be updated at AGM - May 2023
6 | Ensure latest copy of Harrow Parks Forum - Method Statement template is available |  | FoHMP - Method Statement to be developed along Harrow Park Forum Guidelines | Latest Update August 2022 | Harrow Parks Forum / Park User Group | [5 empty] | Document to be updated at AGM - May 2023
7 | Ensure latest copy of Harrow Parks Forum - Accident / Near miss policy is available |  | FoHMP - Accident / Near miss document to be developed along Harrow Park Forum Guidelines | Latest Update August 2022 | Harrow Parks Forum / Park User Group | [5 empty] | Document to be updated at AGM - May 2023
8 | Ensure latest copy of Harrow Parks Forum - Event Sign up sheet is available |  | FoHMP - Event sign Up sheet to be developed along Harrow Park Forum Guidelines | Latest Update August 2022 | Harrow Parks Forum / Park User Group | [5 empty] | Document to be updated at AGM - May 2023
9 | Ensure Public Liability Insurance is in Place |  | This is currently provided by Harrow Council until 30th April 2023 | 2022 Insurance Policy issued | Harrow Council / FoHMP | [5 empty] | Harrow Council will provide Insurance Cover for 2023 / 2024
10 | Ensure Contents Insurance for Storage Container is in place |  | This is currently provided by Harrow Council until April 2023 | 2022 Insurance Policy issued | Harrow Council / FoHMP | [5 empty] | At present it may be necessary for FoHMP to provide our own Insurance from May 2023 (Further Discussions ongoing with Harrow Council)
11 | Ensure Licesnse to Occupy for Storage Container is in place |  | Formal Licesence to be issued | We currently have a without prejodice email from Harrow Council | Harrow Council / FoHMP | [5 empty] | Awaiting Formally signed documents
12 | Ensure Licesnse to Occupy for Pavilion is in place |  | Formal Licesence to be issued | This is currently being reviewed by Harrow Council origional request issued in July 2021 | Harrow Council / FoHMP | [5 empty] | Awaiting Formally signed documents
10 | Improve Boundary defences | A | Some additional vechile incursion defences are required along the Headstone Lane boundary |  | Harrow Council
|  | B | If practical a 1 metre buffer zone should be provided between boundary fencing and plants / shrubs |  | Harrow Council / FoHMP
11 | Improve physical activity and increase participation into casual exercise across a range of age groups |  | Headstone Manor Park has in the past been used for Football, Cricket, Basketball, and Tennis. FoHMP to make contact with clubs to ensure they are aware of our plans and see if they were willing and able to help. Ensuring litter was not left behind after their sessions would be something we could ask their help with! | Initial contact made with Sports Clubs | FoHMP | [5 empty] | Ongoing
|  |  | Tennis Courts | LTA Funding - Harrow Council have completed the public consultation and approval of the proposal was agreed at the Cabinet meeting in November 2022 | [6 empty] | Awaiting Harrow Council to appoint LTA Contractor - Target Spring 2023
|  | A | Contact West Harrow Cricket Club |  | FoHMP
|  | B | Contact Bessborough Cricket Club |  | FoHMP
|  | C | Contact Headstone Manor Youth Football club |  | FoHMP
|  | D | Contact Pinner Albion Football club |  | FoHMP
|  | E | Mind Angels | Over 60's Mobility Classes & QiGong booked every Tuesday from March till September | FoHMP | [5 empty] | Confirmed for 2023
|  | F | Yoga Yatra Sudio | Walk & Yoga booked for Every Wednesday & Sunday from March till September | FoHMP | [5 empty] | Confirmed for 2023
|  |  | Yoga Yatra Sudio | Walk & Yoga booked for Every Wednesday & Sunday from October to February (In the Pavilion) | FoHMP | [5 empty] | Confirmed for 2023
|  | G | Soham Yoga London | Walk & Yoga booked for Every Saturday from March till September | FoHMP | [5 empty] | Confirmed for 2023
12 | Make Playground area dog free to protect children |  | No dogs allowed signage to be displayed around the Playground |  | Harrow Council
13 | Make Playground area Bicycle free to protect children |  | No bicycles allowed signage to be displayed around the Playground |  | Harrow Council
14 | Make Park itself more dog friendly |  | Designate areas where Dogs can be let of there leads |  | Harrow Council / FoHMP
15 | Make access paths safe and secure | B | Install some lighting on the path from the bridge leading to Bessbourgh Cricket Pavilion to the bridge at the end of the Picnic area |  | Harrow Council
16 | Make Basketball hoop area surface safer. The surface is in a poor state of repair. With very litte drainage facility |  | The Basketball area is in need of an overhaul (New Back board & Line Marking) |  | Harrow Council / FoHMP | [5 empty] | FoHMP to obtain costings for bespoke backboard
17 | Make Headstone Manor Park less prone to Drug Misuse |  | There is some drug related litter around the carparks & pavilions | Consider the installation of signage to these areas | Harrow Council / FoHMP | [5 empty] | FoHMP have finalised a Crime Prevention survey and report - Issue February 2023

## Development
The Friends of Headstone Manor Park - 5 Year Action Plan (01st Jamuary 2023 to 31st December 2027)
Development
Item | Objective | Sub-Item | Description | Current Status | Resources Required | Year |  |  |  |  | Deliverables
[6 empty] | 2023 | 2024 | 2025 | 2026 | 2027
1 | The Moat Café Wild Flower Meadow |  | Provision of Wild Flower Meadow from the Public Toilet Block to the Bridge to Bessbourgh Cricket Club | Approved in MMP. Log boundary to prevent mowing has been installed along with interpretation signage & Habitat piles | FoHMP | [5 empty] | Area to be strimmed in March and turned over before sowing with seeds
2 | The Yeading Brook Grove |  | Provision of Native Bulbs and Wild Flowers along the Brook edge from the Picnic area to Hugs and Giggles Nursery | Approved in MMP. Some snowdrops have been planted along with interpretation signage & Habitat piles | FoHMP
3 | Pinner View Wildlife Area |  | Mowing regime modfied in 5 Year Management & Maintenance Plan | Approved in MMP Area to be cut annually and arisings removed interpretation signage installed | FoHMP | [5 empty] | Annual cut in October
4 | John Hollingdale Grove |  | Provision of Native Perennial & Annual Bulbs along with shrubs to atract Pollinators, Moths & Butterflies | Approved in MMP Interpretation signage installed | FoHMP
5 | Parkside Way Entrance |  | Improvement to Entrance Drought tollerant plants as 6 No. Ornamental Cherry Trees | Draft proposal to be submitted to Harrow Council | FoHMP
6 | Headstone Manor Copse - Pinner View |  | Implementation of Ecology Report dated 2022 | Harrow Council to seek funding for these works
7 | Hedging. There are some areas around the periphery of Headstone Manor Park where there is no vegetation between the park and people's garden fence boundary |  | Plant new hedging in these spots. Should be native species; hawthorn, blackthorn, beech etc. which will improve the overall look of the periphery, provide nesting sites for wild birds and provide extra security for householders bordering Headstone Manor Park | Approved in MMP | FoHMP | [5 empty] | Tree Whips to be source from the Woodland Trust (Every 6 Months Delivery March & November)
8 | Water Supply for watering new trees and other plants | A | Provision of water supplies across the Park. Harrow Council to investigate |  | Harrow Council
|  | B | Discuss option of providing an outdoor tap at the Moat Café. Requires discussions with Headstone Manor & Museum |  | Harrow Council / FoHMP
|  | C | Provision of Water Butts at Public Toilets for Water harvesting | Approved in MMP | FoHMP
9 | Consultation with Residents and Park Users |  | Gauge local opinion before making any changes. Particularly in the case of hedging at the bottom of gardens or planting trees that may eventually cast shadows into gardens |  | FoHMP
10 | New Bins |  | Bins to be provided to new benches were practicle FoHMP to liase with Harrow Council (2 new bins in Wetland Area & 2 new bins on circular route ) |  | Harrow Council / FoHMP
11 | "Mulch Store" |  | Create a small storeage area for chippings to mulch new trees/bedding plants/bulbs etc. |  | Harrow Council / FoHMP
12 | "Compost Area" |  | Create an area for onsite Composting |  | Harrow Council / FoHMP